## Project Budget
Budget: One day workshop
[7 empty] | TARGET BUDGET | ACTUAL/FINAL SPEND | UNDER/ OVER
[7 empty] | 456670 | 0 | 456670
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE | HOURS | RATE | UNITS | $/UNIT(S)
Milestone 1: TRAINING PROGRAM FOR NEW TEAMS
Task 1: NEW TEAMS RECRUITMENT | HR manager | 80 | 20 | 10 | 20 | 15000 | 16800 |  | -16800
Task 2: Define Tasks and Responsibilities for the new team | PRODUCTION TEAM LEADER | 20 | 20 | 0 | 0 |  | 400 |  | -400
Task 3: Select Trainers from the Existing Team | Existing Team manager | 40 | 20 | 3 | 50 |  | 950
Task 4: Provide Theoretical Training | Team leaders | 29 | 30 |  |  |  | 870
Task 5: Implement On-the-Job Training | Team leaders | 30 | 25 |  |  |  | 750
Task 6: Monitor and Evaluate Performance | Operational manager | 60 | 20 |  |  |  | 1200 |  | -1200
[6 empty] | Total | 20970 | 0
Milestone 2: CONTRACT WITH THE MATERIAL COMPANY(POWER PARTS)
Task 1: CONTRACT Negotiation and Setting Terms: | Project Manager | 20 | 40 |  |  | 0 | 800 |  | -800
Task 2: Drafting the Contract | Legal Department | 22 | 30 |  |  | 0 | 660 |  | -660
Task 3: Legal Review | Legal Department | 6 | 15 |  |  | 0 | 90 |  | -90
Task 4: Signing and Documentation | Project Manager | 1 | 50 |  |  | 0 | 50 |  | -50
[6 empty] | Total | 1600 | 0
Milestone 3: BUILD NEW WORKSHOP BUILDING
Task 1: Research and send RFPs to vendors. | Procurement Specialist | 80 | 50 | 10 | 500 |  | 9000 |  | -9000
Task 2: SELECT VENDOR AND DEVOLOP CONTRACT | LEGAL TEAM WITH PROJECT MANAGMENT | 20 | 25 |  | 0 |  | 500 |  | -500
Task 3: CONSTRUCTION PHASE | VENDOR | 300 | 40 | 20 | 4000 |  | 92000 |  | -92000
Task 4: FINISHING THE BUILDING FACILITIES | VENDOR | 200 | 300 | 13 | 3000 |  | 99000
Task 4: Acceptance Inspection. And monitoring | production team leader | 80 | 25 |  | 0 |  | 2000
[6 empty] | Total | 202500 | 0
Milestone 4: EQUIPMENT PURSHASING
Task 1: dentify required equipment | electrical and mechanical departments managers | 20 | 50 | 2 | 5000 |  | 11000 |  | -11000
Task 2: Research Equipment Vendors | procurment specialist | 80 | 50 |  |  |  | 4000 |  | -4000
Task 3: Purchase Equipment | procurment specialist | 90 | 40 | 30 | 4000 |  | 123600
Task 4: Install Equipment | equipment suppliers | 80 | 50 | 13 | 3000 |  | 43000 |  | -43000
[6 empty] | Total | 181600 | 0
Reserve buffer | [6 empty] | 50000
TOTAL | [6 empty] | 456670 | 0