## Gantt Chart
Gantt Chart
TITLE: One day workshop | [6 empty] | COMPANY NAME: |  |  | SAKKARY MOTORS
PROJECT MANAGER:OMAR SAKKARY | [6 empty] | CREATION DATE: |  |  | 25/10
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [30 empty] | PHASE TWO | [42 empty] | PHASE THREE | [16 empty] | PHASE FOUR
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 15
[7 empty] | APRIL | [19 empty] | MAY | [20 empty] | JUNE | [21 empty] | JULY | [22 empty] | AUGUST | [20 empty] | SEPTEMPER
[8 empty] | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R
1 | TRAINING PROGRAM FOR NEW TEAMS | [6 empty] | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 17 | 18 | 19 | 20 | 21 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25
1.1 | NEW TEAMS RECRUITMENT | HR manager | 4/6/2025 | 6/1/2025 | 60 | 0% | bar: S 6 to JUNE S 1
1.2 | Define Tasks and Responsibilities for the new team | PRODUCTION TEAM LEADER | 6/2/2025 | 6/8/2025 | 7 | 0% | bar: JUNE M 2 to JUNE S 8
1.3 | Select Trainers from the Existing Team | Existing Team manager | 6/9/2025 | 6/16/2025 | 7 | 0% | bar: JUNE M 9 to JUNE M 16; AUGUST M 11 to AUGUST W 20
1.4 | Provide Theoretical Training | Team leaders | 8/11/2025 | 8/20/2025 | 14 | 0% | bar: AUGUST R 21 to SEPTEMPER M 22
1.5 | Implement On-the-Job Training | Team leaders | 8/21/2025 | 9/22/2025 | 30 | 0%
1.6 | Monitor and Evaluate Performance | Operational manager | 6/17/2025 | 8/12/2025 |  | 0% | bar: JUNE T 17 to SEPTEMPER M 22
2 | CONTRACT WITH THE MATERIAL COMPANY
2.1 | CONTRACT Negotiation and Setting Terms: | Project Manager | 4/6 | 4/14 | 7 | 0% | bar: S 6 to M 14
2.2 | Drafting the Contract | Legal Department | 4/15 | 4/19 | 4 | 0% | bar: T 15 to S 19
2.3 | Legal Review | Legal Department | 4/21 | 4/23 | 3 | 0% | bar: T 21 to R 24
2.4 | Signing and Documentation | Project Manager | 4/25 | 4/26 | 2 | 0% | bar: S 25 to M 26
3 | BUILD NEW WORKSHOP BUILDING
3.1 | Research and send RFPs to vendors. | Procurement Specialist | 4/15 | 4/30 | 14 | 0% | bar: S 13 to W 30
3.2 | SELECT VENDOR AND DEVOLOP CONTRACT | LEGAL TEAM WITH PROJECT MANAGMENT | 5/1 | 5/15 | 14 | 0% | bar: MAY R 1 to MAY R 15
3.3 | CONSTRUCTION PHASE | VENDOR | 5/18 | 7/18 | 60 | 0% | bar: MAY S 18 to JULY R 17
3.4 | FINISHING THE BUILDING FACILITIES | VENDOR | 7/19 | 8/10 | 21 | 0% | bar: JULY S 20 to AUGUST S 10
3.5 | •Acceptance Inspection. And monitoring | production team leader | 8/13 | 8/20 | 7 | 0% | bar: AUGUST M 11 to AUGUST R 21
4 | EQUIPMENT PURSHASING
4.1 | Identify required equipment | electrical and mechanical departments managers | 6/17 | 6/24 | 7 | 0% | bar: JUNE T 17 to JUNE T 24
4.2 | Research Equipment Vendors | procurment specialist | 6/25 | 7/10 | 14 | 0% | bar: JUNE W 25 to JULY R 10
4.3 | Purchase Equipment | procurment specialist | 7/11 | 7/24 | 14 | 0% | bar: JULY S 13 to JULY R 24
4.4 | Install Equipment | equipment suppliers | 8/10 | 8/26 | 16 | 0% | bar: AUGUST S 10 to AUGUST T 26