## Template - Phase 2
Al-Sakkary Motors
NEW WORKSHOP | Product manager | Operation manager | PURCHASING MANAGER | Mechanical department manager | Electrical department manager | Hr manager | Marketing manager | Finance manager | PRODUCTION TEAM LEADER | Sales manager | HR TEAM LEADER | MARKETING TEAM LEADER | procurment specialist
PHASE 2
Task/Deliverable
BUILDING OF THE MAINTENANCE CENTER (VENDOR CONTRACT) | A | C | C | C | I | I | I | R | R | I | I | I | C
TRAINING PROGRAM FOR NEW TEAMS | I | C | I | R | R | A | I | I | I | I | R | C | I
CONTRACT WITH THE MATERIAL COMPANRY(POWER PARTS) | C | C | A | C | I | R | C | I | C | c | I | I | I
NEW EQUIPMENT PURCHASING | C | I | A | R | R | I | I | C | C | C | I | I | C