## WBS Spreadsheet
Al-Sakkary Motors
Deliverables | Task ID | Task | Owner | Duration (days) | Notes
TRAINING PROGRAM FOR NEW TEAMS | 1.1 | NEW TEAMS RECRUITMENT | HR manager | 60
| 1.2 | Define Tasks and Responsibilities for the new team | PRODUCTION TEAM LEADER | 7 | identifying the core tasks needed from the new team and the required skills.
| 1.3 | Select Trainers from the Existing Team | Existing Team manager | 7 | Choose a few members from the existing team to act as trainers, ensuring they can transfer knowledge effectively.
| 1.4 | Provide Theoretical Training | Team leaders | 14 | Trainers from the Existing Team conduct the theoretical training sessions, covering essential processes, tools, and policies.
| 1.5 | Implement On-the-Job Training | Team leaders | 30 | Have the new team work alongside the existing team, ensuring they have opportunities to try tasks on their own.
| 1.6 | Monitor and Evaluate Performance | Operational manager | among the process | Track the new team’s progress and perform regular assessments to ensure the training is on track.
CONTRACT WITH THE MATERIAL COMPANY(POWER PARTS) | 2.1 | CONTRACT Negotiation and Setting Terms: | Project Manager | 7 | Agree on the contract details with the company, including the type of auto parts, prices, order quantities, and delivery schedules.
| 2.2 | Drafting the Contract | Legal Department | 4 | Prepare an official contract that includes all agreed-upon terms, with clear details on the rights and obligations of both parties.
| 2.3 | Legal Review | Legal Department | 3 | Review the contract with a lawyer or legal department to ensure it complies with laws and is in the company’s best interest.
| 2.4 | Signing and Documentation | Project Manager | 2 | Once all details are agreed upon, both parties sign the contract, and ensure any necessary documentation or notarization if required.
BUILD NEW WORKSHOP BUILDING | 3.1 | Research and send RFPs to vendors. | Procurement Specialist | 14
| 3.2 | SELECT VENDOR AND DEVOLOP CONTRACT | LEGAL TEAM WITH PROJECT MANAGMENT | 14
| 3.3 | CONSTRUCTION PHASE | VENDOR | 60
| 3.4 | FINISHING THE BUILDING FACILITIES | VENDOR | 21
| 3.5 | •Acceptance Inspection. And monitoring | production team leader | 7
EQUIPMENT PURSHASING | 4.1 | Identify required equipment | electrical and mechanical departments managers | 7
| 4.2 | Research Equipment Vendors | procurment specialist | 14
| 4.3 | Purchase Equipment | procurment specialist | 14
| 4.4 | Install Equipment | equipment suppliers | 16

## Sheet1
i | Task | Duration (days) | Dependencies
1 | NEW TEAMS RECRUITMENT | 60 | 0
2 | Define Tasks and Responsibilities for the new team | 5 | 1
3 | Select Trainers from the Existing Team | 5 | 2
4 | Provide Theoretical Training | 10 | 3
5 | Implement On-the-Job Training | 30 | 2
6 | Monitor and Evaluate Performance | among the process | 5,2
7 | Tender CONTRACT Negotiation and Setting Terms: | 5 | 6
8 | Drafting the Contract | 3 day | 7
9 | Legal Review | 2 | 8,4
10 | Signing and Documentation | 2 | 9
11 | Research and send RFPs to vendors. | 12 | 10
12 | SELECT VENDOR AND DEVOLOP CONTRACT | 10 | 11
13 | CONSTRUCTION PHASE | 50
14 | FINISHING THE BUILDING FACILITIES | 20
15 | •Acceptance Inspection. And monitoring | 7
16 | Identify required equipment | 5
17 | Research Equipment Vendors | 10
18 | Purchase Equipment | 10
19 | Install Equipment | 15